## Cover
VWO Login Dashboard
Test Plan
app.vwo.com
Project | VWO Login Dashboard (app.vwo.com)
Document | Test Plan
Version | 1.0
Prepared By | QA Team
Date | 18 Oct 2026
Status | Draft

## Test Plan
VWO Login Dashboard - Test Plan
Version 1.0 ¦ Prepared by QA Team ¦ 18 Oct 2026
Objective
The goal of this test plan is to ensure the quality, functionality, security, and reliability of the VWO Login Dashboard hosted at app.vwo.com.
The VWO Login Dashboard is the critical entry point for users accessing VWO's experimentation, personalization and analytics platform, used by over 4,000 brands across 90 countries for A/B testing, conversion rate optimization (CRO) and user behavior analysis.
Testing will validate a secure, intuitive and efficient login experience that connects users to the platform while maintaining enterprise-grade security standards and an exceptional user experience for digital marketers, product managers, UX designers, developers and enterprise teams.
Success Metrics Tracked
• Login Success Rate: target 95%+ successful authentication attempts.
• Page Load Time: maintain sub-2-second login page loading.
• User Satisfaction: achieve 90%+ user satisfaction scores for the login experience.
Guardrail Metrics
• Zero successful brute force attacks or unauthorized access.
• No unauthorized session hijacking incidents.
• 100% compliance with security audit requirements.
Scope
Scope of the Test Plan for the VWO Login Dashboard:
1. Functional Testing
• Verify the correctness and functionality of all login dashboard features as per the PRD.
• Test login with valid and invalid email/password combinations, Remember Me, account registration and free-trial signup links.
• Validate session management with configurable timeouts, optional Multi-Factor Authentication (2FA) and enterprise Single Sign-On (SSO).
2. Data Validation Testing
• Ensure email and password inputs are validated and invalid requests are rejected.
• Test real-time (on-blur) validation, email format verification with specialized mobile keyboards and password strength indicators.
• Test boundary values for input fields and validate the accuracy of messages returned.
3. Error Handling Testing
• Verify clear, actionable error messages are returned for failed authentication attempts.
• Check error responses for sensitive information disclosure.
• Validate the dashboard's ability to handle unexpected errors gracefully and offer multiple recovery paths.
4. Performance Testing
• Assess the login page response time and load speed under normal and peak loads to identify potential bottlenecks.
• Measure throughput and scalability to support thousands of simultaneous login attempts.
5. Security Testing
• Conduct security assessments to identify vulnerabilities such as SQL injection, XSS and brute force attacks.
• Validate HTTPS/SSL/TLS enforcement and end-to-end encryption of authentication data.
• Verify encrypted password storage using industry-standard hashing, secure session token generation, rate limiting, and GDPR/CCPA compliance.
6. Integration Testing
• Verify seamless transition to the main VWO dashboard after successful authentication.
• Test analytics integration for login success/failure tracking, customer support integration and third-party identity providers (Google, Microsoft, SAML/OAuth SSO).
• Verify data consistency and context preservation from previous sessions.
7. Compatibility Testing
• Test the login dashboard on different platforms, browsers and devices to ensure cross-compatibility of the responsive, mobile-optimized interface.
8. Accessibility Testing
• Validate screen reader support (ARIA labels), full keyboard navigation, high contrast mode and clickable labels.
• Verify WCAG 2.1 AA compliance and inclusive design for all user abilities.
9. Load Testing
• Evaluate the dashboard's behavior under high concurrent user loads to ensure stability and 99.9% availability.
10. Regression Testing
• Conduct regression testing after bug fixes or updates to ensure existing login functionality remains intact.
11. Edge Case Testing
• Test extreme and boundary scenarios (e.g., very long inputs, special characters and rapid repeated submissions) to identify potential issues.
12. Concurrency Testing
• Assess behavior when multiple users attempt to log in simultaneously and when a single account is used across multiple sessions.
13. Ad Hoc Testing
• Perform exploratory testing to identify hidden defects or usability issues in the login flow.
14. Usability Testing
• Evaluate the user-friendliness and ease of use of the login experience (auto-focus, clickable labels, loading states and minimal friction).
15. Continuous Integration and Deployment (CI/CD) Testing
• Validate the login dashboard's behavior within the CI/CD pipeline to ensure smooth deployments.
16. Rate Limiting Testing
• Check the dashboard's adherence to rate-limiting rules and request throttling to prevent abuse and brute force attacks.
17. Third-Party Integration Testing
• Validate enterprise SSO (SAML, OAuth), social login (Google, Microsoft) and marketing/onboarding integrations for smooth functioning.
18. Internationalization Testing
• Test the login dashboard's behavior with different language settings and locales.
19. Backup and Recovery Testing
• Validate data backup and recovery procedures to ensure authentication data integrity.
20. Documentation Review
• Assess the clarity, completeness and accuracy of the login dashboard documentation.
• Verify that the documentation is in sync with the actual behavior.
It's important to note that the scope of the test plan may evolve during the testing process based on feedback, changing requirements or discoveries during testing. The scope should be reviewed and adjusted accordingly throughout the testing phase to ensure comprehensive coverage of the VWO Login Dashboard.
Inclusions
Login (Sign In)
• Test login with valid credentials and verify successful transition to the VWO dashboard.
• Verify appropriate error responses for invalid credentials, missing/invalid data and locked accounts.
• Validate that Remember Me functions correctly for persistent sessions and that loading states are shown during authentication processing.
Registration and Onboarding
• Verify the free-trial signup call-to-action and account registration link with minimal friction.
• Validate the guided onboarding/context shown after successful registration.
Authentication and Session Management
• Test optional Multi-Factor Authentication (2FA) and enterprise SSO (SAML/OAuth) flows.
• Validate secure session handling, configurable session timeout and secure session token generation.
User Input Validation
• Verify real-time (on-blur) validation, email format verification and password strength indicators.
• Verify auto-focus on the first input field and clickable form labels.
Password Management
• Test the forgot-password flow with secure token generation and email-based recovery.
• Verify enforced password complexity requirements.
Error Handling and Recovery
• Test clear, actionable error messages for authentication failures and multiple account recovery/support paths.
• Verify clear confirmation upon successful login.
Interface and User Experience
• Verify responsive, mobile-optimized design with touch-friendly controls, loading states, auto-focus and clickable labels.
• Verify brand consistency, professional visual design and Light/Dark Mode theme support.
Accessibility
• Verify ARIA labels, full keyboard navigation, screen reader support and high contrast mode (WCAG 2.1 AA).
Security
• Verify HTTPS/SSL/TLS enforcement, end-to-end encryption, secure password hashing, session token security and rate limiting.
Boundary Testing
• Test minimum and maximum allowed values for input fields and values close to the boundaries.
Concurrency Testing
• Test behavior when multiple users perform login/logout and password-reset operations simultaneously.
Data Validation
• Test responses to various validation scenarios (invalid characters, data types and mandatory fields).
Integration Testing
• Verify interaction and data consistency between the login dashboard, the VWO core platform and third-party identity providers.
Regression Testing
• Perform regression tests after fixes or updates to ensure existing login functionality remains intact.
Compatibility Testing
• Test login flows on different platforms, browsers and devices.
Usability Testing
• Evaluate the ease of use of the login flow from an end user's perspective.
CI/CD Testing
• Validate login dashboard changes within the CI/CD pipeline to ensure smooth deployments.
Rate Limiting Testing
• Check adherence to rate-limiting rules to prevent abuse.
Backup and Recovery Testing
• Validate backup and recovery procedures for authentication data.
Test Environments
The following environments, devices and conditions will be used for testing:
Environment URLs
(See sheet: Test Environments)
Supported Platforms
• Windows 10 - Chrome, Firefox and Edge
• Mac OS - Safari Browser
• Android Mobile OS - Chrome
• iPhone Mobile OS - Safari
Test Environment Details
• Operating systems and versions used for testing (Windows 10, macOS, Linux).
• Browsers and versions tested (Google Chrome, Mozilla Firefox, Microsoft Edge, Safari).
• Device types and screen sizes (desktop, laptop, tablet and smartphone).
• Network connectivity and bandwidth available for testing (Wi-Fi, cellular, wired).
• Hardware and software requirements for running test cases (processor, memory, storage).
• Security protocols and authentication methods used to access the test environment (passwords, tokens, certificates).
• Access permissions and roles of team members using the environment (testers, developers, stakeholders).
Defect Reporting Procedure
• Criteria for identifying a defect: deviation from requirements, user experience issues or technical errors.
• Steps for reporting a defect: use the designated template, provide detailed reproduction steps, and attach screenshots or logs.
• Process for triaging and prioritizing defects: assign severity and priority levels and assign them to the appropriate team members for investigation and resolution.
• Tools and systems used for tracking and managing defects: JIRA (defect tracking) and project management tools.
• Roles and responsibilities of the team members involved in the defect reporting process (testers, developers and the test lead).
• Communication channels and frequency for updating stakeholders on defect progress and status.
• Metrics used to measure the effectiveness of the defect reporting process: number of defects found, time taken to resolve them, and the percentage of defects successfully fixed.
Defect Process - Point of Contact (POC)
(See sheet: Defect Reporting)
Tool: JIRA
Test Strategy
Step 1: Test Scenario and Test Case Creation
• The first step is to create test scenarios and test cases for the various features in scope.
• While developing test cases, we will use a number of test design techniques: Equivalence Class Partition, Boundary Value Analysis, Decision Table Testing, State Transition Testing and Use Case Testing.
• We also use our expertise in creating test cases by applying Error Guessing and Exploratory Testing.
• We prioritize the test cases.
Step 2: Testing Procedure When a Testing Request Is Received
• First, we will conduct smoke testing to check whether the various important functionalities of the login dashboard are working.
• We reject the build if smoke testing fails and will wait for a stable build before performing in-depth testing of the application functionalities.
• Once we receive a stable build that passes smoke testing, we perform in-depth testing using the test cases created.
• Multiple test resources will test the same application on multiple supported environments simultaneously.
• We then report the bugs in the bug tracking tool and send development management the defects found on that day in an end-of-day status email.
• As part of testing, we will perform the following types of testing: Smoke Testing and Sanity Testing, Regression Testing and Retesting, Usability Testing, Functionality and UI Testing.
• We repeat test cycles until we get a quality product.
Step 3: Best Practices
• Context Driven Testing - we perform testing as per the context of the given application.
• Shift Left Testing - we start testing from the beginning stages of development itself, instead of waiting for the stable build.
• Exploratory Testing - using our expertise we perform exploratory testing, apart from the normal execution of test cases.
• End to End Flow Testing - we test end-to-end scenarios involving multiple functionalities to simulate end user flows.
Test Schedule
Following is the test schedule planned for the project:
(See sheet: Test Schedule)
2 Sprints to Test the Application.
Test Deliverables
• Test Plan
• Test Scenarios
• Test Cases
• Test Execution Reports
• Defect Reports
• Test Summary Report
Entry and Exit Criteria
The following are the entry and exit criteria for every phase of the Software Testing Life Cycle (STLC):
Requirement Analysis
• Entry Criteria: Once the testing team receives the requirements documents or details about the project.
• Exit Criteria: List of requirements are explored and understood by the testing team; doubts are cleared.
Test Execution
Entry Criteria
• Test scenarios and test case documents are signed off by the client.
• Application is ready for testing.
Exit Criteria
• Test case reports and defect reports are ready.
Test Closure
Entry Criteria
• Test case reports and defect reports are ready.
Exit Criteria
• Test summary reports.
Tools
The following are the list of tools we will be using in this project:
• JIRA Bug Tracking Tool
• Mind map Tool
• Snipping Screenshot Tool
• Word and Excel documents
Risks and Mitigations
The following are the list of possible risks and the ways to mitigate them:
(See sheet: Risks & Mitigations)
Approvals
The team will send different types of documents for client approval, like the following:
• Test Plan
• Test Scenarios
• Test Cases
• Reports
Testing will only continue to the next steps once these approvals are done.

## Test Environments
Name | Env URL
QA | https://app.vwo.com
Pre Prod | https://app.vwo.com

## Defect Reporting
Role | POC
New Frontend | Devesh
Backend | Sonal
Dev Ops | Prajeeth

## Test Schedule
Task | Dates
Creating Test Plan | TBD
Test Case Creation | TBD
Test Case Execution | TBD
Summary Reports Submission Date | TBD

## Risks & Mitigations
Risk | Mitigation
Non-Availability of a Resource | Backup Resource Planning
Build URL is not working | Resources will work on other tasks
Less time for Testing | Ramp up the resources based on the client needs dynamically
Security vulnerability discovered during testing | Immediate triage with the security team, apply patches and re-test before release
Third-party SSO / identity provider unavailability | Coordinate with the provider, use a fallback auth path and retest once available